# Conference Agenda Planner

An illustrative in-person conference from 08:30 to 17:00, using local venue time. It assumes 120 participants at 20 tables of six. Two parallel clinics each hold 60 people at ten tables. This is a planning example, not a report of a delivered event.

Use this editable example to assign real owners, rooms and outputs. Full block instructions and a CSV schedule accompany the online template.

# Objectives

Compare two approaches to a shared professional challenge.

Design a small test each participant can take back to work.

# Outputs

An option sheet per table, recording choices and open questions.

A personal action card with an owner, date and evidence to check.

# Before the day

Confirm one main hall for 120 and two clinic rooms for 60 each. Prebook clinic places, then confirm capacities and accessible routes with the venue.

Assign a lead facilitator, one clinic facilitator per room, a roving helper per clinic and a table recorder. Name registration, AV and follow-up owners.

Provide option sheets, action cards, pens, microphones and an accessible digital copy. Check requested access needs, captions, dietary needs and quiet seating before the day.

Invite one optional ask and offer at check-in. Use only details participants agree to share; keep confidential information off public boards.

Test the routes between rooms. If a move needs more than ten minutes, shorten session content or extend the timetable before publishing it.

# When to adapt this plan

This example is not a staffing or capacity plan for a much larger event. Confirm room limits, staff availability and participant needs locally.

The clinics suit people willing to discuss one shared challenge. A lecture, certification exam or confidential decision meeting needs another design.

This plan assumes everyone is on site. Hybrid delivery needs a separate access, audio and facilitation plan.

# Morning schedule

Local venue time. Durations include the stated changeovers. Replace role names with assigned people before the day.

| Time | Session and location | Output and changeover |
| --- | --- | --- |
| 08:30-09:00 30 min | Arrival and optional asks and offers Foyer ¦ All Owner: Registration lead | Optional introduction request Changeover: Seat by 09:00 |
| 09:00-09:10 10 min | Welcome and the shared challenge Main hall ¦ All Owner: Lead facilitator | Challenge on option sheet Changeover: Stay at tables |
| 09:10-09:40 30 min | Opening keynote Main hall ¦ All Owner: Speaker | One idea to examine Changeover: Stay at tables |
| 09:40-09:48 8 min | Reaction tables Main hall ¦ All Owner: Table recorder | Notes on option sheet Changeover: Stay at tables |
| 09:48-10:00 12 min | Questions to the speaker Main hall ¦ All Owner: Moderator | Clarified questions Changeover: Break starts at 10:00 |
| 10:00-10:20 20 min | Break and room change Foyer to clinics ¦ A or B Owner: Room stewards | No output required Changeover: Arrive by 10:20 |
| 10:20-11:20 60 min | Parallel clinics on two approaches Rooms A and B ¦ A or B Owner: Clinic facilitators | Draft option sheet Changeover: Stay in clinic room |
| 11:20-11:30 10 min | Break Clinic areas ¦ A or B Owner: Room stewards | No output required Changeover: Return to same table |
| 11:30-12:10 40 min | Compare options and constraints Rooms A and B ¦ A or B Owner: Clinic facilitators | Completed option sheet Changeover: Lunch starts at 12:10 |
| 12:10-13:10 60 min | Lunch and optional introductions Dining area ¦ All Owner: Lunch coordinator | Optional connection Changeover: Return to main hall next |

# Afternoon schedule

Local venue time. Durations include the stated changeovers. Replace role names with assigned people before the day.

| Time | Session and location | Output and changeover |
| --- | --- | --- |
| 13:10-13:20 10 min | Return and recap Main hall ¦ All Owner: Lead facilitator | Two approaches recapped Changeover: Stay at tables |
| 13:20-14:00 40 min | Experts examine a shared example Main hall ¦ All Owner: Moderator | Constraints on option sheet Changeover: Break at 14:00 |
| 14:00-14:15 15 min | Break Main hall area ¦ All Owner: Room stewards | No output required Changeover: Return by 14:15 |
| 14:15-15:00 45 min | Design a small test Main hall ¦ All Owner: Lead facilitator | Draft personal action card Changeover: Stay at tables |
| 15:00-15:30 30 min | Peer review Main hall ¦ All Owner: Table recorder | Reviewed action card Changeover: Break at 15:30 |
| 15:30-15:45 15 min | Break Main hall area ¦ All Owner: Room stewards | No output required Changeover: Return by 15:45 |
| 15:45-16:15 30 min | Owners dates and sharing choices Main hall ¦ All Owner: Follow-up owner | Completed personal action card Changeover: Stay at tables |
| 16:15-16:45 30 min | Synthesis from selected examples Main hall ¦ All Owner: Lead facilitator | Approved summary notes Changeover: Stay at tables |
| 16:45-17:00 15 min | Close and agree the review Main hall ¦ All Owner: Follow-up owner | Review date and access route Changeover: Departure at 17:00 |

# Illustrative redesign notes

These comparisons describe a fictional agenda, not measured results from a delivered conference.

Before: A fictional schedule ends its keynote and immediately starts another talk.

After: Keep the 30-minute keynote, add eight minutes of reaction tables and twelve minutes for questions.

Reason: Participants have a defined place to interpret the argument. This does not establish a retention improvement.

Before: A fictional schedule labels lunch as networking without further instructions.

After: Offer optional introductions based on asks and offers, plus open seating.

Reason: Participants can choose a specific conversation without being required to share personal details.

Before: A fictional schedule ends with thanks and an unspecified promise to follow up.

After: Reserve time for action cards, sharing permissions and an agreed review date.

Reason: An owner and evidence question make later follow-up possible. Completion must still be checked.

# Follow up

Before departure, each participant chooses whether to share an action card and receive a follow-up. Keep a private copy available.

Within two working days, the follow-up owner shares only approved option sheets, open questions and the agreed review date.

At the agreed 30-day review, ask what was attempted, what evidence exists and what changed. An intention or a completed survey is not proof of impact.

# Your action record

Action: __________________________________________

Owner: __________________________________________

Date: __________________________________________

Evidence to check: __________________________________________

Review date: __________________________________________

Sharing permission: __________________________________________

Source and full instructions: https://unitedwetransform.com/conference-agenda-template/